## Sheet1
Sprint #1 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item | Warehouse wants to provide inventory stock to HQ | 16 | 16 | All | NOT COMPLETED | overestimating story points and hours
2 | Stock Item List View | Warehouse wants to be able to see their stock | 10 | 10 | All | NOT COMPLETED | overestimating story points and hours
3 | Send Employee Data to HQ | Warehouse wants to provide a list of employees to HQ | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
4 | Receive Stock Data | HQ wants inventory from warehouse | 6 | 6 | All | NOT COMPLETED | overestimating story points and hours
5 | Receive Emplopyee Data | HQ wants to have a list of employees at warehouse | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
6 | Employee List Creation/ View | HQ wants to have a list of employees in the headquarters | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
Sprint #2 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item | Warehouse wants to provide inventory stock to HQ | 16 | 16 | All | NOT COMPLETED | overestimating story points and hours
2 | Stock Item List View | Warehouse wants to be able to see their stock | 10 | 10 | All | NOT COMPLETED | overestimating story points and hours
3 | Send Employee Data to HQ | Warehouse wants to provide a list of employees to HQ | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
4 | Receive Stock Data | HQ wants inventory from warehouse | 6 | 6 | All | NOT COMPLETED | overestimating story points and hours
5 | Receive Emplopyee Data | HQ wants to have a list of employees at warehouse | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
6 | Employee List Creation/ View | HQ wants to have a list of employees in the headquarters | 8 | 8 | All | NOT COMPLETED | overestimating story points and hours
Previous deliveries HQ -> WH
Sprint #3 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item - Warehouse | As a manager at the Warehouse, I would like to be able to store stock items | 16 | 16 | Florin | COMPLETED
2 | Stock Item List View - Warehouse | As a manager at the Warehouse, I would like to be able to check my actual stock inventory | 10 | 10 | Florin | COMPLETED
3 | Store Employee Item - Warehouse | As a manager at the Warehouse, I would like to store employees of the Warehouse | 8 | 8 | Jaume | COMPLETED
4 | Employee Item List View - Warehouse | As a manager at the Warehouse, I would like to see my list of employees. | 6 | 6 | Jaume | COMPLETED
5 | Request products from HQ | As a manager at the Warehouse, I would like a way of requesting products from HQ | 8 | 8 | Kenneth | NOT COMPLETED
6 | Store Employee Item - HQ | As a manager at the HQ, I want to store employees of the HQ | 8 | 8 | Dave | COMPLETED
7 | Previous deliveries log | As a manager at the HQ, I would like to see the previous deliveries to the Warehouse |  |  | Jaume | COMPLETED
8 | HQ check Employee Item at Warehouse | As a manager in HQ, I want to able to see stock inventory data at the Warehouse |  |  | Dave | COMPLETED
9 | HQ check Stock Item at Warehouse | As a manager at the HQ, I want to be able to see all employees in the Warehouse |  |  | Dave | COMPLETED
10 | System notifies on minimum stock | As a manager at the Warehouse, I would like to be notified on minimum stock. |  |  | Kenneth | NOT COMPLETED
11 | System notifies on maximum stock | As a manager at the Warehouse, I would like to be notified on maximum stock. |  |  | Kenneth | NOT COMPLETED
Sprint #4 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 |  | As a manager at the Warehouse, I would like a way of requesting products from HQ |  | 23/05/2019 09 | Jaume
2 |  | As a manager at the Warehouse, I want to be able to edit my list of employees so that I can remove non-working employees.
3 |  | As a manager at the Warehouse I would like to delete Stock Items from Warehouse inventory
4 |  | As a manager at the Headquarter I would like to delete Stock Items from Headquarter inventory
5 |  | NEW-> As a manager at the Headquarter, I want to be able to edit my list of employees so that I can remove non-working employees.
6 |  | Process Report
7
8
9
10
11
Sprint #5 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 |  | Process Report |  |  | Florin
2 |  | As a manager at the Shop, I need to request and receive products from Warehouse so I can maintain to avoid lack of inventory. |  |  | Jaume
3 |  | NEW ->> As a manager at the Shop, I would like to input and store all my sales units so I can have an overview of my Shop's sales efficiency |  |  | Kenneth
4 |  | As a manager at the Shop, I would like to see my stock inventory at the shop so I can have an overview |  |  | Kenneth
5 |  | The system should synchronize data between clients. |  |  | Jaume
6 |  | Add Stock Item to Shop Inventory
7
8
9
10
11

## Sheet2
PRODUCT Backlog
# | User Stories | Story Points | Remaining |  |  | User Stories
1 | As a manager at the Warehouse, I would like to be able to store stock items | 5 | 2 |  | 1 | As a manager at the Warehouse, I would like to be able to store stock items
2 | As a manager at the Warehouse, I would like to be able to check my actual stock inventory | 5 | 2 |  | 2 | As a manager at the Warehouse, I would like to be able to check my actual stock inventory
3 | As a manager at the Warehouse, I would like to store employees of the Warehouse | 4 | 2 |  | 3 | As a manager at the Warehouse, I would like to store employees of the Warehouse
4 | As a manager in HQ, I want to able to see stock inventory data at the Warehouse | 4 | 2 |  | 4 | As a manager in HQ, I want to able to see stock inventory data at the Warehouse
5 | As a manager at the HQ, I want to be able to see all employees in the Warehouse | 4 | 2 |  | 5 | As a manager at the HQ, I want to be able to see all employees in the Warehouse
6 | As a manager at the HQ, I want to store employees of the HQ | 2 | 2 |  | 6 | As a manager at the HQ, I want to store employees of the HQ
8 | As a manager at the shop, I want to store all the sales of the products | 4 |  |  | 8 | As a manager at the shop, I want to store all the sales of the products
9 | As a manager at the shop, I want to see all the sales of the products | 2 |  |  | 9 | As a manager at the shop, I want to see all the sales of the products
10 | As a manager at the shop, I want to store all stock items | 4 |  |  | 10 | As a manager at the shop, I want to store all stock items
11 | As a manager at the shop, I want to see all the products in stock | 4 |  |  | 11 | As a manager at the shop, I want to see all the products in stock
12 | As manager at the shop, I want to be able to store employees | 4 |  |  | 12 | As manager at the shop, I want to be able to store employees
13 | As a manager at the shop, I want to be able to edit my employees | 2 |  |  | 13 | As a manager at the shop, I want to be able to edit my employees
14 | As a a manager at the shop, I want to be able to see my employees | 4 |  |  | 14 | As a a manager at the shop, I want to be able to see my employees
15 | As a manager at the shop, I would like to have a way of requesting products from HQ | 6 |  |  | 15 | As a manager at the shop, I would like to have a way of requesting products from HQ
16 | As a manager at the Warehouse, I would like a way of requesting products from HQ | 6 |  | x | 16 | As a manager at the Warehouse, I would like a way of requesting products from HQ
17 | As a manager at the Warehouse, I would like to be notified on minimum and maximum stock. | 2 |  | x | 17 | As a manager at the Warehouse, I would like to be notified on maximum stock.
18 | As a manager at the Warehouse, I would like to have the space allocated for products in the Warehouse | 8 |  |  | 18 | As a manager at the Warehouse, I would like to be notified on minimum stock.
19 | As a manager at the HQ, I would like to see the previous deliveries to the Warehouse | 4 |  | x | 19 | As a manager at the HQ, I would like to see the previous deliveries to the Warehouse
20 | As a manager at the Warehouse, I would like a way of checking previous deliveries to the shop | 4 |  |  | 20 | As a manager at the Warehouse, I would like a way of checking previous deliveries to the shop
21 | As a manager at the HQ, I want to check the sales from the shop | 3 |  |  | 21 | As a manager at the HQ, I want to check the sales from the shop
22 | As a manager at the HQ, I want to check the stock from the shop | 3 |  |  | 22 | As a manager at the HQ, I want to check the stock from the shop
23 | As a manager at the HQ, I want to see the list of employees from the shop | 3 |  |  | 23 | As a manager at the HQ, I want to see the list of employees from the shop
24 | As a manager at the HQ, I would like a way of predicting sales in the shop | 8 |  |  | 24 | As a manager at the HQ, I would like a way of predicting sales in the shop
25 | As a manager at the HQ, I would like to have a way of predicting stock at the shop | 8 |  |  | 25 | As a manager at the HQ, I would like to have a way of predicting stock at the shop
26 | As a manager at the HQ, I would like to have a way of predicting stock at the warehouse | 8 |  |  | 26 | As a manager at the HQ, I would like to have a way of predicting stock at the warehouse
27 | As a manager at the HQ, I would like a way of obtaining sales performance analysis | 12 |  |  | 27 | As a manager at the HQ, I would like a way of obtaining sales performance analysis
28 | As a manager at the HQ, I would like a way of obtaining product performance analysis | 12 |  |  | 28 | As a manager at the HQ, I would like a way of obtaining product performance analysis
[5 empty] | 29 | As a manager at the Warehouse, I would like to have the space allocated for products in the Warehouse
[5 empty] | 30 | As a manager at the HQ, I would like to see the deliveries in progress to the Warehouse
[5 empty] | 31 | As a manager at the HQ, I would like to see the completed deliveries to the Warehouse
[5 empty] | 32 | As a manager at the WH, I would like to see the deliveries in progress from the HQ
[5 empty] | 33 | As a manager at the WH, I would like to see the completed deliveries from the HQ
[5 empty] | 34 | As a manager at the WH, I would like to see the deliveries in progress to the Retailer
[5 empty] | 35 | As a manager at the WH, I would like to see the completed deliveries to the Retailer
[5 empty] | 36 | As a manager at the Shop, I would like to see the deliveries in progress from the WH
[5 empty] | 37 | As a manager at the Shop, I would like to see the completed deliveries from the WH
[5 empty] | 38 | As a manager at the Warehouse, I would like to be able to see my employees work history.
[5 empty] | 39 | As a manager at the Shop, I would like to be able to see my employees work history.
[5 empty] | 40 | As a manager at the HQ, I would like to be able to see my employees work history.
[5 empty] | 41 | As a manager at the Warehouse, I would like a way to check the stock waste.
[5 empty] | 42 | As a manager at the HQ, I would like to implement discount cards for all the employees from HQ, WH & Shop for internal purchases. (visitor pattern)
As a manager at the WH, I would like to see my list of employees.

## LOOK HERE!
WAREHOUSE
HQ
As a manager at the Warehouse, I would like a way of requesting products from HQ | As a manager in HQ, I want to able to see stock inventory data at the Warehouse
As a manager at the Warehouse, I would like to be notified on maximum stock. | As a manager at the HQ, I want to be able to see all employees in the Warehouse
As a manager at the Warehouse, I would like to be notified on minimum stock. | As a manager at the HQ, I want to store employees of the HQ
As a manager at the Warehouse, I would like a way of checking previous deliveries to the shop | As a manager at the HQ, I would like to see the previous deliveries to the Warehouse
As a manager at the WH, I would like to see the deliveries in progress from the HQ | As a manager at the HQ, I want to check the sales from the shop
As a manager at the WH, I would like to see the completed deliveries from the HQ | As a manager at the HQ, I want to check the stock from the shop
As a manager at the WH, I would like to see the deliveries in progress to the Retailer | As a manager at the HQ, I want to see the list of employees from the shop
As a manager at the WH, I would like to see the completed deliveries to the Retailer | As a manager at the HQ, I would like a way of predicting sales in the shop
As a manager at the Warehouse, I would like a way to check the stock waste.
As a manager at the Warehouse, I would like to be able to see my employees work history. | As a manager at the HQ, I would like a way of obtaining sales performance analysis
NEW!!!! -> LOG ON MINIMUM AND MAXIMUM NOTIFICATIONS | As a manager at the HQ, I would like to implement discount cards for all the employees from HQ, WH & Shop for internal purchases. (visitor pattern)
As a manager at the HQ, I would like a way of obtaining product performance analysis
SHOP | As a manager at the Warehouse, I would like to have the space allocated for products in the Warehouse?????
As a manager at the shop, I want to store all the sales of the products | As a manager at the HQ, I would like to see the deliveries in progress to the Warehouse
As a manager at the shop, I want to see all the sales of the products | As a manager at the HQ, I would like to see the completed deliveries to the Warehouse
As a manager at the shop, I want to store all stock items | INEW (Sprint 4) -> As a manager at the HQ I wouldlike to approve OR DENY deliveries to the Warehouse
As a manager at the shop, I want to see all the products in stock
As manager at the shop, I want to be able to store employees
As a manager at the shop, I want to be able to edit my employees | DONE
As a a manager at the shop, I want to be able to see my employees |  | As a manager at the Warehouse, I would like to be able to store stock items
As a manager at the Warehouse, I would like to be able to check my actual stock inventory
As a manager at the Shop, I would like to see the deliveries in progress from the WH |  | As a manager at the Warehouse, I would like to store employees of the Warehouse
As a manager at the Shop, I would like to see the completed deliveries from the WH |  | As a manager at the WH, I would like to see my list of employees.
As a manager at the Shop, I would like to be able to see my employees work history. |  | As a manager at the HQ, I would like to see the previous deliveries to the Warehouse

## New backlog
# | WAREHOUSE | Priority | # | SHOP | Priority
1 | As a manager at the Warehouse, I need to request products from Headquarters to keep my stock levels optimal. - needs testing + doc | 4 | 1 | NEW ->> As a manager at the Shop, I would like to input and store all my sales units so I can have an overview of my Shop's sales efficiency | ?
2 | As a manager at the Warehouse, I need to be notified on maximum stock on requests so I don't exceed capacity | ? | 2 | As a manager at the Shop, I would to be able to check and see my sales so I can have an overview | ?
3 | As a managder at the Warehouse, I need to be notified on minimum stock so I don't lack stock inventory for deliveries. | ? | 3 | As a manager at the shop, I would like to have all my stock items stored so I can share this info with Headquarter | ?
4 | As a manager at the Warehouse, I need to check previous deliveries to the Shop so I can have an overview of deliveries. | ? | 4 | As a manager at the Shop, I would like to be able to see all my stored stock items so I can have an overview of my stock inventory levels | ?
5 | As a manager at the Warehouse, I want to be able to check the deliveries in progress that are incoming from HQ so I can decide on future deliveries from Warehouse to the Shop. | ? | 5 | As a manager at the Shop, I would like to store my employee info so I can fulfill human resources requirements | ?
6 | As a manager at the Warehouse, I want to be able to confirm the deliveries that have been sent from HQ to Warehouse to avoid any misunderstandings. | ? | 6 | As a manager at the Shop, I would like to see the list of employees from my Shop for further reporting or overview. | ?
7 | As a manager at the Warehouse, I would like to check the deliveries in progress to the Shop so I can have an overview on the process. | ? | 7 | As a manager at the Shop, I would like to be able to edit and remove employees so I can maintain a clean database of active employees | ?
8 | As a manager at the Warehouse, I would like to check the completed deliveries from the Warehouse to the Shop so I can decide on future requests of products from HQ. | ? | 8 | As a manager at the Shop, I would like to be able to see my employees history so I can have an overview over employees productivity | ?
9 | As a manager at the Warehouse, I would like to check the status on the amount of expired products so I can make my stock inventory more efficient and reduce waste. | ? | 9 | As a manager at the Shop, I need to request products and receive from Warehouse so I can maintain to avoid lack of inventory. | 5
10 | As a manager at the Warehouse I would like to see the work history and performance of my employees so I can keep track on productivity. | ? | 10 | As a manager at the Shop, I need to have an overview of incoming deliveries from the Warehouse so I can have an overview. | ?
11 | NEW-> As a manager at the Warehouse, I want to be able to edit my list of employees so that I can remove non-working employees. | 4 | 11 | As a manager at the Shop, I would like to see my stock inventory at the shop so I can have an overview | ?
12 | NEW ->> As a manager at the Warehouse I would like to delete Stock Items from Warehouse inventory | 4 | 12 | NEW ->>> Add Stock Item to Shop Inventory | ?
13 |  |  | 13 |  | ?
14 |  |  | 14 |  | ?
?
?
# | HEADQUARTERS | Priority |  |  | ?
1 | As a manager at the Headquarter, I want to check the stock inventory at the Warehouse to have control over process or to replace functions for holidays | ?
2 | As a manager at the Headquarter, I want to check the list of employees at the Warehouse so I can have an overview over the business unit | ?
3 | As a manager at the Headquarter, I would like to store my list of employees with info so I can have a clear overview over my human resources. | ?
4 | As a manager at the Headquarter, I would like to be able to edit my list of employees so that I can remove non-working employees. | ?
5 | As a manager at the Headquarter, I want to be able to see the previous deliveries to the Warehouse so I can have an overview over this business process | ?
6 | As a manager at the Headquarter, I want to be able to see the deliveries in progress to the Warehouse so I can have an overview over this business process | ?
7 | As a manager at the Headquarter, I would like to be able to check the sales from Shop so I can have an overview. | ?
8 | As a manager at the Headquarter, I would like to be able to check the stock inventory from the Shop so I can have an overview. | ?
9 | As a manager at the Headquarter, I would like to be able to check the list of employees from the Shop so I can have an overview over this business unit. | ?
10 | As a manager at the Headquarter, I would like a way to predict the upcoming sales at the Shop so I can ensure the availability of the products | ?
11 | As a manager at the Headquarter, I would like a way of obtaining the sales performance analysis from the Shop so I can ensure profitability/ product category. | ?
12 | As amanager at the Headquarter, I would like to implement a discount system for all companie's employee's whenever they make purchases in the shop so I can increase employee's benefits and satisfaction | ?
13 | As a manager at the Headquarter, I would like to obtain product performance analysis so I can ensure profitability/ product. | ?
14 | As a manager at the Headquarter, I would like to have an overview over the deliveries in progress so I can keep an accurate track on my business process. | ?
| NEW ->> As a manager at the Headquarter I would like to delete Stock Items from Headquarter inventory | 4
| NEW-> As a manager at the Headquarter, I want to be able to edit my list of employees so that I can remove non-working employees. | 4